## Phase 1
Sr. No. | Tasks | Estimated Time ( In Hrs ) | Status | Expected Date | Actual Time ( In Hrs ) | Notes
1 | Pre Devlopment
1.1 | Solutioning | 5 | Done | 2017-04-10 | 5
1.2 | Devlopment Env Setup ( Linux & Mysql ) | 4 | Done | 2017-04-10 | 4
1.3 | Repository Setup | 0.5 | Done | 2017-04-10 | 0.5
2 | Front End PHP - UI
2.01 | UI - Login Page | 3 | Done | 2017-04-10 | 3
2.02 | PHP - Login Page | 3 | Done | 2017-04-10 | 3
2.03 | UI - Doctor Listing & Filter | 4 | Done | 2017-04-10 | 6 | Except Filters
2.04 | PHP - Doctor Listing & Filter | 5 | WIP | 2017-04-10 | 5
2.05 | UI - Doctor Data Uploading | 5 | Done | 2017-04-10 | 5
2.06 | PHP - Doctor Data Uploalding & processing | 8 | WIP | 2017-07-10
2.07 | UI - Player Log Listing & Filter | 3 |  | 2017-07-10
2.08 | PHP - Player Log Listing & Filter | 5 |  | 2017-07-10
2.09 | UI - Player Log Data Uploading | 3 |  | 2017-10-10
2.1 | PHP - Player Log Data Uploading & Processing | 8 |  | 2017-10-10
2.11 | UI - Device File Count Listing | 3 |  | 2017-11-10
2.12 | PHP - Device File Count Listing | 5 |  | 15/10/2017
2.13 | UI - Device File Count Data Uploading | 3 |  | 15/10/2017
2.14 | PHP - Device File Count Data Uploading & Processing | 5 |  | 15/10/2017
3 | Tableau Tasks (Starting after completion of 2.08)
3.01 | Calculate & Identify the logics used to Identify Online, Offline, etc | 7 |  | 2017-08-10
3.02 | Create Map (Includes Color, Labels) | 7 |  | 2017-10-10
3.03 | Create Pie Graph | 2 |  | 2017-12-10
3.04 | Add Filters | 4 |  | 2017-12-10
3.05 | Design Dashbard | 16 |  | 16/10/2017
3.06 | Design Dashboard 2 | 15