## Sheet1
3 | Tableau Tasks (Starting after completion of 2.08)
3.01 | Calculate & Identify the logics used to Identify Online, Offline, etc | 7 |  | 2017-08-10
3.02 | Create Map (Includes Color, Labels) | 7 |  | 2017-10-10
3.03 | Create Pie Graph | 2 |  | 2017-12-10
3.04 | Add Filters | 4 |  | 2017-12-10
3.05 | Design Dashbard | 16 |  | 16/10/2017
Dahsboard 2
1.01 | Creating Map | 3 | Done | 20/10/2017 | 3
1.02 | Add filters | 1 | WIP | 20/10/2017
1.03 | Add Labels | 2 | WIP | 20/10/2017
1.04 | Add Pie Chart | 2 | WIP | 20/10/2017
1.05 | Create Dashboard | 7 | WIP | 20/10/2017
Dashborad 3
2.01 | Add filters | 5 | Done | 24/10/2017 | 5
2.02 | Add Labels | 3 | Done | 24/10/2017 | 3
2.03 | Create Data Table | 7 | Done | 24/10/2017 | 7
2.04 | Create Dashboard | 10 | Done | 24/10/2017 | 10
Upload to Server
3.01 | This needs to checked and configured | 5 | Done | 25/10/2017 | 5
Dashboard 4,5,6
4.01 | Same Logic as Dashboard 3 | 30 |  | 2017-02-11
Status Change
7.01 | Understand the logic and get the calculations | 10 |  | 2017-07-11 |  | Tasks related to "STATUS Change" needs to be done on priority before Dashboard 7. This change may delay the deveopment of Dashboard 7.
7.02 | Apply changes on all the dashboards | 6 |  | 2017-07-11
7.03 | Checking if the filters are working fine | 2 |  | 2017-07-11
| Total Hours | 129