## Phase 1
Sr. No. | Tasks | Estimated Time ( In Hrs ) | Status | Expected Date | Actual Time ( In Hrs ) | Notes
1 | Pre Devlopment
1.1 | Solutioning | 5 | Done | 2017-04-10 | 5
1.2 | Devlopment Env Setup ( Linux & Mysql ) | 4 | Done | 2017-04-10 | 4
1.3 | Repository Setup | 0.5 | Done | 2017-04-10 | 0.5
2 | Front End PHP - UI
2.01 | UI - Login Page | 3 | Done | 2017-04-10 | 3
2.02 | PHP - Login Page | 3 | Done | 2017-04-10 | 3
2.03 | UI - Doctor Listing & Filter | 4 | Done | 2017-04-10 | 6
2.04 | PHP - Doctor Listing & Filter | 5 | Done | 2017-04-10 | 5
2.05 | UI - Doctor Data Uploading | 5 | Done | 2017-04-10 | 5
2.06 | PHP - Doctor Data Uploalding & processing | 8 | Done | 2017-07-10 | 8
2.07 | UI - Player Log Listing & Filter | 3 | Done | 2017-07-10 | 3
2.08 | PHP - Player Log Listing & Filter | 5 | Done | 2017-07-10 | 7
2.09 | UI - Player Log Data Uploading | 3 | Done | 2017-10-10 | 3
2.1 | PHP - Player Log Data Uploading & Processing | 8 | Done | 2017-10-10 | 8
2.11 | UI - Device File Count Listing | 3 | Done | 2017-11-10 | 3
2.12 | PHP - Device File Count Listing | 5 | Done | 15/10/2017 | 5
2.13 | UI - Device File Count Data Uploading | 3 | Done | 15/10/2017 | 3
2.14 | PHP - Device File Count Data Uploading & Processing | 5 | Done | 15/10/2017 | 5
3 | Tableau Tasks (Starting after completion of 2.08)
3.01 | Calculate & Identify the logics used to Identify Online, Offline, etc | 7 | Done | 2017-08-10 | 9
3.02 | Create Map (Includes Color, Labels) | 7 | Done | 2017-10-10 | 7
3.03 | Create Pie Graph | 2 | Done | 2017-12-10 | 2
3.04 | Add Filters | 4 | Done | 2017-12-10 | 4
3.05 | Design Dashbard | 16 | Done | 16/10/2017 | 16
3.06 | Design Dashboard 2 | 15 | WIP | 20/10/2017

## Phase 2
Sr. No. | Tasks | Estimated Time ( In Hrs ) | Status | Expected Date | Actual Time ( In Hrs ) | Notes
Front-End Tasks
2.11 | UI - PLaylist Listing | 3 | Done | 17-10-2017 | 3
2.12 | PHP - Playlist Listing | 5 | Done | 18-10-2017 | 5
2.13 | UI -Playlist Data Uploading | 3 | Done | 19-10-2017 | 3
2.14 | PHP - Playlist Data Uploading & Processing | 5 | Done | 20-10-2017 | 5
2.01 | Toggle with detailed view of doctors masters | 10 | Done | 22-10-2017 | 10
2.02 | View details of specific doctor | 4 | Done | 23-10-2017 | 4
2.03 | Edit Doctor with edit form | 8 | WIP | 25-10-2017
2.04 | Add new doctor form to add new doctor | 6 | WIP | 27-10-2017
3.01 | Adding more filters to player logs | 3 | WIP | 28-10-2017
3.02 | Checking for redundant data for player logs while uploading | 2 | Done | 28-10-2017 | 2
3.03 | Download data for player logs | 4 | WIP | 29-10-2017
Tableau Tasks
Dahsboard 2
1.01 | Creating Map | 3 | Done | 20/10/2017 | 3
1.02 | Add filters | 1 | WIP | 20/10/2017
1.03 | Add Labels | 2 | WIP | 20/10/2017
1.04 | Add Pie Chart | 2 | WIP | 20/10/2017
1.05 | Create Dashboard | 7 | WIP | 20/10/2017
Dashborad 3
2.01 | Add filters | 5 | Done | 24/10/2017 | 5
2.02 | Add Labels | 3 | Done | 24/10/2017 | 3
2.03 | Create Data Table | 7 | Done | 24/10/2017 | 7
2.04 | Create Dashboard | 10 | Done | 24/10/2017 | 10
Upload to Server
3.01 | This needs to checked and configured | 5 | Done | 25/10/2017 | 5 | This is done on other tableau account as there is some issue on existing online account.
Dashboard 4,5,6
4.01 | Same Logic as Dashboard 3 | 30
5.01 | Designing the viz | 11
6.01 | Dashboard 7 | 30