## Phase 1
Sr. No. | Tasks | Estimated Time ( In Hrs ) | Status
1 | Pre Devlopment
1.1 | Solutioning | 5
1.2 | Devlopment Env Setup ( Linux & Mysql ) | 4
1.3 | Repository Setup | 0.5
2 | Front End PHP - UI
2.1 | UI - Login Page | 3
2.2 | PHP - Login Page | 3
2.3 | UI - Doctor Listing & Filter | 4
2.4 | PHP - Doctor Listing & Filter | 5
2.5 | UI - Doctor Data Uploading | 5
2.6 | PHP - Doctor Data Uploalding & processing | 8
2.7 | UI - Player Log Listing & Filter | 3
2.8 | PHP - Player Log Listing & Filter | 5
2.9 | UI - Player Log Data Uploading | 3
2.1 | PHP - Player Log Data Uploading & Processing | 8